## Man power
CIVIL WORK MANPOWER DEPLOYMENT REPORT
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ.
AGENCY : AR ENGINEERING COMPANY
09.07.2018
MAN POWER DEPLOYMENT (TODAY)
STRUCTURE WISE DEPLOYMENT
Sr.No. | CATEGORY | UNIT | ETP TANK/RO BUILDING
1 | Unskiled labour | no | 15
2 | Mason | no | 5
3 | Carpenter+barbender | no | 12
4 | Fitter | no | 12
5 | JCB Operator | no | 0
6 | Tractor drivers | no | 0
7 | TM | no | 0
8 | Concrete pump | no | 0
44

## work report
CIVIL WORK REPORT
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : AR ENGINEERING COMPANY
07.07.2018
WORK REPORT
Sr.No. | ITEM | UNIT | QUANTITIES |  |  |  | TODAY PLANING | REMAKS
|  |  | TOTAL SCOPE | PREVIOUS PROGRESS | TODAY PROGRESS | TOTAL PROGRESS
1 | ETP /RO BUILDING
a | Footing excavation | Nos. | 20 | 20 | 0 | 20 | 0
b | PCC in footings | Nos. | 20 | 20 | 0 | 20 | 0
c | RCC footings | Nos. | 20 | 20 | 0 | 20 | 0
d | Colums up to plinth | Nos. | 20 | 19 | 0 | 19 | 0
e | Columns above plinth | Nos. | 20 | 0 | 0 | 0 |  | REINFORCEMENT
f | Plinth beam | Nos. | 35 | 15 | 20 | 35 |  | work in progress
g | Soling under floor | Cum. | 32 | 0 | 0 | 0
h | PCC under floor | Cum. | 21 | 0 | 0 | 0
i | Slab +3.40m lvl | cum | 0 | 0 |  | 0 | 0
j | Column Above Slab 1st lift | Nos. | 0 | 0 |  | 0
k | Column Above Slab 2nd lift | Nos. | 0 | 0 |  | 0
l | Plaster | sqm | 0 | 0 | 0 | 0
m | Lintel Beam | Cum | 0 | 0 |  | 0
n | Slab +7.900m lvl | Cum. | 0 | 0 |  | 0
2 | MFG FEED TANK RO REJECT TANK
a | Footing excavation | m3 | 50 | 50 |  | 50 | 0
b | Soling | m3 | 28 | 28 | 0 | 28 |  | REINFORCEMENT & SHUTTERING
c | PCC in footings | m3 | 9.5 | 9.5 | 0 | 9.5 | 0 | work in progress
d | RCC footings | m3 | 62 | 62 | 0 | 62 | 0
e | RCC foR Tank | M3 | 110 | 0 | 0 | 0 | 0
3 | MEE BUILDING
a | Footing excavation | m3 | 155 | 155 | 0 | 155 | 0
b | PCC in footings | m3 | 7 | 7 | 0 | 7 | 0
c | RCC footings | m3 | 45 | 45 | 0 | 45 | 0
d | RCC FOR COLUMN | m3 | 12 | 12 | 0 | 12 | 0

## machinery
CIVIL MACHINERY REPORT
AGENCY : AR ENGINEERING COMPANY
07.07.2018
Machinery Deployment
Sr.No. | CATEGORY | UNIT | QTY. DEPLOYED
1 | JCB | no | 0
2 | Tractor | no | 0
3 | TM | no | 0
4 | Batching plant | no | 0
5 | Concrete pump | no | 0

## material report
CIVIL MATERIAL REPORT
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : AR ENGINEERING COMPANY
07.07.2018
MATERIAL REPORT
Sr.No. | ITEM | UNIT | QTY. RECEIVED
|  |  | PREVIOUS RECEIVED | TODAY RECEIVED | CUMMULATIVE RECEIVED
1 | TMT BAR
2 | 8mm | Mt. | 5.675 | 11.755 | 17.43
3 | 10mm | Mt. | 29.55 | 5.05 | 34.6
4 | 12mm | Mt. | 17.8 | 3.65 | 21.45
5 | 16mm | Mt. | 28.87 | 31.096 | 59.966
6 | 20mm | Mt. | 3.655 | 4.96 | 8.615
7 | 25 mm | Mt. | 1.12 |  | 1.12
8 | 32 mm | Mt. | 0 |  | 0
143.181

## Qty .plan
CIVIL QUALITY PLAN
PROJECT :NITRIC ACID PLANT -Rev-03-(Updated)
PHASE : Construction & Commissioning
AGENCY : AR ENGINEERING COMPANY
07.07.2018
S.No | Item Description | Unit | Total scope as per BOQ | Additional scope expected in BOQ | Released till date | Cumulative Achieved till last month | This month progress - june 2018 |  |  |  | Cumulative achieved since inception.
[7 empty] | Planned for this month | Till date achieved in this month | Achieved today | Cumulative Achieved till date in this month |  | 2018-07-18
|  | 1 | 2 |  |  | 3 | 4 | 5 | 6 | 7 = 5+6 | 3 + 7
AS PER BOQ
1 | Concrete
a | Concrete -M30 | CUM | 454 | - | 360.5 | 237 | 150 | 123.5 | 0 | 123.5 | 360.5 | 123.5
b | M20 | CUM | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | M10 | CUM | 84 |  | 37.2 | 37.2 | 0 | 7 | 0 | 7 | 44.2 | 7

## Fabrication Report (hidden)
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE: 14.05.2018
PROGRESS : 12.05.2018 & 13.05.2018
STRUCTURAL STEEL FABRICATION REPORT
PROJECT :- DFPCL |  |  |  |  | LOCATION :- DAHEJ | [7 empty] | DATE:- | 12.05.2018
BUILDING | SCOPE | UNIT | MATERIAL RECEIVED | FABRICATION |  |  | ERECTION |  |  | ALIGNMENT |  |  | BLASTING | PAINTING
|  |  |  | PREV. | TODAY | CUMM. | PREV. | TODAY | CUMM. | PREV. | TODAY | CUMM. |  | PRIMER | MIO | FINAL COAT
103A - WNA Storage Tank | 5 | MT |  | 5 |  | 5 | 2 |  | 2 |  |  | 0 | 5 | 5 | 5 | 5
103B - CNA Storage Tanks/Pump area | 50 | MT |  |  |  | 0 |  |  | 0 |  |  | 0
103E - WNA / CNA/SNA Tanker Loading Bay | 20 | MT |  | 5 | 0.5 | 5.5 |  | 1 | 1 |  |  | 0 | 3 | 2 | 2 | 2
104A -Caustic, Sulphuric Storage | 3 | MT |  | 1.5 |  | 1.5 |  |  | 0 |  |  | 0 | 1.5 | 1.5 | 1.5 | 1.5
104C -Ammonia Storage | 25 | MT |  |  |  | 0 |  |  | 0 |  |  | 0
104E -SNA Storage | 2 | MT |  | 1.3 |  | 1.3 |  |  | 0 |  |  | 0 | 1.3 | 1.3 | 1.3 | 1.3
105A/C - Air Compressor, Air Dryer | 13 | MT |  | 12.9 |  | 12.9 | 6 | 4 | 10 |  |  | 0 | 12.9 | 12.9 | 12.9 | 12.9
105B - VAM Unit | 15 | MT |  | 15 |  | 15 | 15 |  | 15 | 15 |  | 15 | 15 | 15 | 15 | 15
106C - TG Building | 75 | MT |  | 41.8 |  | 41.8 |  |  | 0 |  |  | 0 | 40.6 | 30.5 | 27 | 27
107B - Raw Water Treatment Plant |  | MT |  |  |  | 0 |  |  | 0 |  |  | 0
108C - DM Plant | 2.5 | MT |  | 2.5 |  | 2.5 | 2.5 |  | 2.5 |  |  | 0 | 2.5 | 2.5 | 2.5 | 2.5
108D - DM STORAGE | 5 | MT |  |  |  | 0 |  |  | 0 |  |  | 0
109 - Cooling Tower with Pumps | 3 | MT |  |  |  | 0 |  |  | 0 |  |  | 0
110 - Process Substation/DG ROOM | 2 | MT |  |  |  | 0 |  |  | 0 |  |  | 0
TOTAL | 220.5 |  |  | 85 | 0.5 | 85.5 | 25.5 | 5 | 30.5 | 15 | 0 | 15 | 81.8 | 70.7 | 67.2 | 67.2
Description | FABRICATION Current Manpower | ERECTION Current Manpower |  | Remarks :
Fitter | 3 | 1
Welder | 3 | 1
Gas Cutter | 2
Grinder | 2
Driller | 2
Helper | 1
Rigger | 6 | 4
Tack welder | 1
Sandblasting | 0
Painting | 2
Foremen | 1
Total | 23 | 6