## DPR
| DAILY PROGRESS REPORT |  |  |  |  | DATE | 06.09.2018
DEEPAK FERTILISERS & PERTOCHEMICALS COPORATION LIMITED
ISGEC HEAVY ENGINEERING LIMITED
PROJECT : 40 TPH AFBC BOILER
SL.NO | DESCRIPTION OF ITEM | UOM | SCOPE | Progress |  |  |  | Remarks
|  |  |  | Till Previous day | Today | Cumm | Balance
1.0 | STRUCTURE
1.1 | Columns | Kg | 25152.73 | 25152.73 | 0 | 25152.73 | 0 | Completed
1.2 | Canopy Strurcture | Kg | 20777.92 | 18252.73 | 0 | 18252.73 | 2525.19
1.3 | Beams and bracing | Kg | 56383.81 | 55907.38 | 0 | 55907.38 | 476.43
1.4 | Grating, Staircase, chequred Plate, Hand Rail | Kg | 15925.34 | 10935.569 | 0 | 10935.569 | 4989.771
| Sub Total | Kg | 118239.8 | 110248.409 | 0 | 110248.409 | 7991.391
2.0 | BOILER PRESSURE PARTS
2.1 | Steam drum | Kg | 11303.18 | 10391.09 | 0 | 10391.09 | 912.09
2.2 | Front Water Wall Panels | Kg | 6798.83 | 6798.83 | 0 | 6798.83 | 0 | Completed
2.3 | Rear Water Wall Panels | Kg | 4671.89 | 4671.89 | 0 | 4671.89 | 0 | Completed
2.4 | RHS Water wall Panels | Kg | 5722.54 | 5722.54 | 0 | 5722.54 | 0 | Completed
2.5 | LHS Water Wall Panels | Kg | 5761.1 | 5761.1 | 0 | 5761.1 | 0 | Completed
2.6 | Convective Super Heater Coil | Kg | 13627.34 | 13393.46 | 0 | 13393.46 | 233.88
2.7 | Radiant Super Heater Coil | Kg | 8355.41 | 8355.41 | 0 | 8355.41 | 0 | Completed
2.8 | Economiser Coils | Kg | 21996.84 | 21996.84 | 0 | 21996.84 | 0 | Completed
2.9 | Bed Coil | Kg | 10837.75 | 10837.75 | 0 | 10837.75 | 0 | Completed
| Sub Total | Kg | 89074.88 | 87928.91 | 0 | 87928.91 | 1145.97
3 | BUCK STAY and seismic supports | [5 empty] | 0
3.1 | Buckstay | Kg | 5188.28 | 4900.8 | 0 | 4900.8 | 287.48
3.2 | Seismic support | Kg | 747.94 | 747.94 | 0 | 747.94 | 0 | Completed
| Sub Total | Kg | 5936.22 | 5648.74 | 0 | 5648.74 | 287.48
4 | DUCTING AND CASING
4.1 | FD duct | Kg | 9947.644 | 3250.49 | 0 | 3250.49 | 6697.154
4.2 | PA duct | Kg | 3142.492 | 2189.62 | 0 | 2189.62 | 952.872
4.3 | SA duct | Kg | 2146.35 | 888.09 | 0 | 888.09 | 1258.26
4.4 | FG duct | Kg | 21845.6805 | 5100.23 | 0 | 5100.23 | 16745.4505
4.5 | Air Box | Kg | 12959.84 | 12830.73 | 0 | 12830.73 | 129.11
4.7 | APH Casing | Kg | 2269.895 | 2081.24 | 0 | 2081.24 | 188.655
4.8 | Economiser casing | Kg | 4048.025 | 3219.12 | 0 | 3219.12 | 828.905
4.9 | Furnace bottom Sealing | Kg | 2215.37 | 121 | 0 | 121 | 2094.37
4.1 | Cover plates and doors | Kg | 2357.15 | 1852.47 | 0 | 1852.47 | 504.68
4.11 | Hopper | Kg | 3613.065 | 3386.83 | 0 | 3386.83 | 226.235
4.12 | Foundation bolts | Kg | 2198.34 | 1705.61 | 0 | 1705.61 | 492.73
| Sub Total | Kg | 66743.8515 | 36625.43 | 0 | 36625.43 | 30118.4215
5 | EQUIPMENT | [5 empty] | 0
5.1 | De-aerator | Kg | 10050.5 | 0 | 8474.48 | 8474.48 | 1576.02
5.2 | Air heater | Kg | 15809.02 | 15809.02 | 0 | 15809.02 | 0 | Completed
5.3 | FD Fan | Kg | 4340 | 4098 | 0 | 4098 | 242
5.4 | ID Fan | Kg | 5060 | 4759 | 0 | 4759 | 301
5.5 | PA Fan | Kg | 2300 | 2118 | 0 | 2118 | 182
5.6 | BFP | Kg | 13930 | 0 | 0 | 0 | 13930
5.7 | Feeders | Kg | 8735 | 8235 | 0 | 8235 | 500
5.8 | Coal Bunker 1 | Kg | 19725.07 | 19725.07 | 0 | 19725.07 | 0
5.9 | Coal Bunker 2 | Kg | 16941.28 | 16941.28 | 0 | 16941.28 | 0
5.1 | Lime stone Bunker | Kg | 10571.88 | 10571.88 | 0 | 10571.88 | 0
5.11 | Bed Material Bunker | Kg | 3955.535 | 3955.535 | 0 | 3955.535 | 0
5.12 | Fuel feeding system' | Kg | 13262.19 | 4087.25 | 837.47 | 4924.72 | 8337.47
5.13 | ESP | Kg | 125257.14 | 120894.4233 | 0 | 120894.4233 | 4362.7167
5.14 | CBD Tank | Kg | 724.34 | 724.34 | 0 | 724.34 | 0 | Completed
5.15 | LP Dosing | Kg | 1050 | 0 | 0 | 0 | 1050
5.17 | HP Dosing | Kg | 1250 | 1250 | 0 | 1250 | 0 | Completed
| Sub Total | Kg | 252961.955 | 213168.7983 | 9311.95 | 222480.7483 | 30481.2067
6 | PIPING | [5 empty] | 0
6.1 | Intergral Piping | Kg | 14916.49 | 14916.49 | 0 | 14916.49 | 0 | Completed
6.2 | Integral piping support | Kg | 1701.8705 | 1701.8705 | 0 | 1701.8705 | 0 | Completed
6.3 | Cooling water piping | Kg | 1059.98 | 0 | 0 | 0 | 1059.98
6.4 | Boiler House Piping | Kg | 22180.61 | 410 | 0 | 410 | 21770.61
6.5 | Boiler House Piping supports | Kg | 10932.7295 | 0 | 0 | 0 | 10932.7295
| Sub Total | Kg | 50791.68 | 4747.25 | 0 | 17028.3605 | 33763.3195
7 | NDT | nos | 120 | 120 | 0 | 120 | 0 | Completed
8 | REFRACTORY | kg | 37000 | 1950 | 0 | 1950 | 35050
9 | INSULATION | SQM | 3820 | 0 | 0 | 0 | 3820
| Boiler Total |  | 620748.3865 | 460317.5373 | 9311.95 | 481910.5978 | 138837.7887
11 | Coal Handling system
11.1 | BC-1 | Kg | 32546.83 | 28777.26 | 0 | 28777.26 | 3769.57
11.2 | BC-2 | Kg | 5868.26 | 2935.6 | 0 | 2935.6 | 2932.66
11.3 | BC-3 and RBC | Kg | 20573.63 | 9436.67 | 210 | 9646.67 | 10926.96
| FHS Total |  | 58988.72 | 41149.53 | 210 | 41359.53 | 17629.19
12 | Ash handling system | Kg | 43829 | 35086 | 180 | 35266 | 8563
| AHS Total | Kg | 43829 | 35086 | 180 | 35266 | 8563
| Grand Total | KG | 723566.1065 | 536553.0673 | 9701.95 | 558536.1278 | 165029.9787 |  | 0
| ISGEC STAFF |  |  | Manpower Samarth Engineering |  |  |  | Aditya insulation
| Category | Quantity |  | Category |  | Quantity |  | Category | Quantity
| Site Incharge | 1 |  | Site Incharge |  | 1 |  | Site Incharge | 1
| Erection Engineer | 1 |  | Engineer |  | 1 |  | Welder | 1
| QC Engineer | 1 |  | QC Engineer |  | 1 |  | Scaffolder | 4
| Electrical Engineer | 1 |  | Electrician |  | 1 |  | Helper | 1
| Instrumentation Engineer | 1 |  | Supervisors |  | 1 |  | Welder | 1
| EHS officer | 1 |  | Safety Officer |  | 1 |  | Total | 8
| Store Keeper | 1 |  | Fitter |  | 8
| CHS erection engineer | 1 |  | Mill Wright |  | 0 |  | Saarc Refractory
| Total | 7 |  | IBR welder |  | 0 |  | Site Incharge | 1
|  |  |  | Welder |  | 8 |  | Scaffolder | 2
|  |  |  | Gas Cutter |  | 2 |  | Carpenter | 1
|  |  |  | Grinder |  | 2 |  | Mason | 1
|  |  |  | Foreman |  | 1 |  | Helper | 3
|  |  |  | Rigger |  | 14 |  | Total | 8
|  |  |  | Helper |  | 10
|  |  |  | Kalasi |  | 5 |  | Star Instruments
|  |  |  | Stores |  | 1 |  | Category | Quantity
|  |  |  | Hydra operator |  | 1 |  | Supervisor | 1
|  |  |  | Crane operator + assistant |  | 2 |  | Welder | 2
|  |  |  | Total |  | 60 |  | fitter | 1
[8 empty] | Technican | 1
[8 empty] | Khalasi | 1
[8 empty] | Helper | 1
[8 empty] | Total | 7
83

## E&I
| DAILY PROGRESS REPORT |  |  |  |  | DATE | 06.09.2018
DEEPAK FERTILISERS & PERTOCHEMICALS COPORATION LIMITED
ISGEC HEAVY ENGINEERING LIMITED
PROJECT : 40 TPH AFBC BOILER
SL.NO | DESCRIPTION OF ITEM | UOM | SCOPE | Progress |  |  |  | Remarks
|  |  |  | Till Previous day | Today | Cumm | Balance
1.0 | Instrumentation
1.1 | Pressure Transmitter | Nos. | 15 | 0 | 0 | 0 | 15
1.2 | Differential Pressure Transmitter | Nos. | 26 | 0 | 0 | 0 | 26
1.3 | Level Switch / Transmitter | Nos. | 18 | 0 | 0 | 0 | 18
1.4 | Temperature Transmitter | Nos. | 8 | 0 | 0 | 0 | 8
1.5 | Pressure Switch | Nos. | 22 | 0 |  |  | 22
1.6 | Limit Switch (InBuilt with Actuator, CV, Damper etc.) | Nos. | 24 | 0 | 0 | 0 | 24
1.7 | Junction box/ PDB/ hooter along with cable gland | Nos. | 41 | 0 | 0 | 0 | 41
1.8 | Cable Tray | Mtr. | 1800 | 0 | 0 | 0 | 1800
1.9 | Cables | Mtr. | 11480 | 0 | 0 | 0 | 11480
1.1 | Level Gauges | Nos. | 8 | 0 | 0 | 0 | 8
1.11 | Pressure Gauges | Nos. | 57 | 0 | 0 | 0 | 57
1.12 | Temperature Gauges | Nos. | 8 | 0 | 0 | 0 | 8
1.13 | Temperature Elements | Nos. | 71 | 0 | 0 | 0 | 71
1.14 | Flow Elements |  | 4 | 0 | 0 | 0 | 4
1.15 | Control valves/ dampers | Nos. | 19 | 0 |  | 0 | 19
1.16 | On- Off valve / Actuator | Nos. | 29 | 0 | 0 | 0 | 29
1.17 | Switches | Nos. | 36 | 0 | 0 | 0 | 36
1.19 | UPS SYSTEM | Nos. | 1 | 0 | 0 | 0 | 1
1.2 | DCS SYSTEM | Nos. | 1 | 0 | 0 | 0 | 1 | Shifting is under progress
1.21 | SWAS System | Nos. | 1 | 0 | 1 | 1 | 0 | Completed
1.22 | O2 Analyzer (SET) | Nos. | 1 | 0 | 0 | 0 | 1
1.23 | AHS Pneumatic Panels | Nos. | 6 | 0 | 0 | 0 | 6
1.24 | Air compressor system | Nos. | 2 | 0 |  | 0 | 2
1.25 | Metal Detector | Nos. | 1 | 0 | 0 | 0 | 1
1.26 | Magnetic Seperator | Nos. | 1 | 0 | 0 | 0 | 1
1.27 | Metal Detector | Nos. | 1 | 0 | 0 | 0 | 1
2 | Electrical
2.1 | Transformer forESP | Nos. | 4 | 0 | 4 | 4 | 0 | Completed
2.2 | MCC Panels | Nos. | 2 | 0 | 0 | 0 | 2
2.3 | VFD Panels | Nos. | 5 | 0 | 0 | 0 | 5
2.4 | TRCC Panels | Nos. | 4 | 0 | 4 | 4 | 0 | Completed
2.5 | Installation of LCS/JB/LPBS | Nos. | 74 | 0 | 0 | 0 | 74
2.6 | Erection of cable tray | Kg | 1600 | 53 | 0 | 53 | 1547
2.7 | Erection of cable tray bend | Nos. | 255 | 0 | 0 | 0 | 255
2.8 | Earthing strip | Kg | 2500 | 0 | 0 | 0 | 2500
2.9 | Steel structure support | Kg | 4960 | 1400 | 0 | 1400 | 3560
2.1 | Laying of Power & Control cables | Mtrs. | 17020 | 0 |  | 0 | 17020
2.11 | Glanding & Termination of LV Cables (Panel gland Both Side) | nos. | 2706 | 0 | 0 | 0 | 2706

## CCT
SL.NO | DESCRIPTION OF ITEM |  |  | UOM | SCOPE | Progress |  |  |  | Remarks
|  | Start Date | End Date |  |  | Till Previous day | Today | Cumm | Balance
1.0 | STRUCTURE | 2018-09-11 | 2018-10-07
1.1 | Columns |  |  | Kg | 25152.73 | 25152.73 | 0 | 25152.73 | 0 | Completed
1.2 | Canopy Strurcture |  |  | Kg | 20777.92 | 18252.73 | 0 | 18252.73 | 2525.19
1.3 | Beams and bracing |  |  | Kg | 56383.81 | 55907.38 | 0 | 55907.38 | 476.43
1.4 | Grating, Staircase, chequred Plate, Hand Rail |  |  | Kg | 15925.34 | 10935.569 | 0 | 10935.569 | 4989.771
| Sub Total |  |  | Kg | 118239.8 | 110248.409 | 0 | 110248.409 | 7991.391
2.0 | BOILER PRESSURE PARTS
2.1 | Steam drum |  |  | Kg | 11303.18 | 10391.09 | 0 | 10391.09 | 912.09
2.2 | Front Water Wall Panels |  |  | Kg | 6798.83 | 6798.83 | 0 | 6798.83 | 0 | Completed
2.3 | Rear Water Wall Panels |  |  | Kg | 4671.89 | 4671.89 | 0 | 4671.89 | 0 | Completed
2.4 | RHS Water wall Panels |  |  | Kg | 5722.54 | 5722.54 | 0 | 5722.54 | 0 | Completed
2.5 | LHS Water Wall Panels |  |  | Kg | 5761.1 | 5761.1 | 0 | 5761.1 | 0 | Completed
2.6 | Convective Super Heater Coil |  |  | Kg | 13627.34 | 13393.46 | 0 | 13393.46 | 233.88
2.7 | Radiant Super Heater Coil |  |  | Kg | 8355.41 | 8355.41 | 0 | 8355.41 | 0 | Completed
2.8 | Economiser Coils |  |  | Kg | 21996.84 | 21996.84 | 0 | 21996.84 | 0 | Completed
2.9 | Bed Coil |  |  | Kg | 10837.75 | 10837.75 | 0 | 10837.75 | 0 | Completed
| Sub Total |  |  | Kg | 89074.88 | 87928.91 | 0 | 87928.91 | 1145.97
3 | BUCK STAY and seismic supports | [7 empty] | 0
3.1 | Buckstay |  |  | Kg | 5188.28 | 4900.8 | 0 | 4900.8 | 287.48
3.2 | Seismic support |  |  | Kg | 747.94 | 747.94 | 0 | 747.94 | 0 | Completed
| Sub Total |  |  | Kg | 5936.22 | 5648.74 | 0 | 5648.74 | 287.48
4 | DUCTING AND CASING
4.1 | FD duct |  |  | Kg | 9947.644 | 3250.49 | 0 | 3250.49 | 6697.154
4.2 | PA duct |  |  | Kg | 3142.492 | 2189.62 | 0 | 2189.62 | 952.872
4.3 | SA duct |  |  | Kg | 2146.35 | 888.09 | 0 | 888.09 | 1258.26
4.4 | FG duct |  |  | Kg | 21845.6805 | 5100.23 | 0 | 5100.23 | 16745.4505
4.5 | Air Box |  |  | Kg | 12959.84 | 12830.73 | 0 | 12830.73 | 129.11
4.7 | APH Casing |  |  | Kg | 2269.895 | 2081.24 | 0 | 2081.24 | 188.655
4.8 | Economiser casing |  |  | Kg | 4048.025 | 3219.12 | 0 | 3219.12 | 828.905
4.9 | Furnace bottom Sealing |  |  | Kg | 2215.37 | 121 | 0 | 121 | 2094.37
4.1 | Cover plates and doors |  |  | Kg | 2357.15 | 1852.47 | 0 | 1852.47 | 504.68
4.11 | Hopper |  |  | Kg | 3613.065 | 3386.83 | 0 | 3386.83 | 226.235
4.12 | Foundation bolts |  |  | Kg | 2198.34 | 1705.61 | 0 | 1705.61 | 492.73
| Sub Total |  |  | Kg | 66743.8515 | 36625.43 | 0 | 36625.43 | 30118.4215
5 | EQUIPMENT | [7 empty] | 0
5.1 | De-aerator |  |  | Kg | 10050.5 | 0 | 8474.48 | 8474.48 | 1576.02
5.2 | Air heater |  |  | Kg | 15809.02 | 15809.02 | 0 | 15809.02 | 0 | Completed
5.3 | FD Fan |  |  | Kg | 4340 | 4098 | 0 | 4098 | 242
5.4 | ID Fan |  |  | Kg | 5060 | 4759 | 0 | 4759 | 301
5.5 | PA Fan |  |  | Kg | 2300 | 2118 | 0 | 2118 | 182
5.6 | BFP |  |  | Kg | 13930 | 0 | 0 | 0 | 13930
5.7 | Feeders |  |  | Kg | 8735 | 8235 | 0 | 8235 | 500
5.8 | Coal Bunker 1 |  |  | Kg | 19725.07 | 19725.07 | 0 | 19725.07 | 0
5.9 | Coal Bunker 2 |  |  | Kg | 16941.28 | 16941.28 | 0 | 16941.28 | 0
5.1 | Lime stone Bunker |  |  | Kg | 10571.88 | 10571.88 | 0 | 10571.88 | 0
5.11 | Bed Material Bunker |  |  | Kg | 3955.535 | 3955.535 | 0 | 3955.535 | 0
5.12 | Fuel feeding system' |  |  | Kg | 13262.19 | 4087.25 | 837.47 | 4924.72 | 8337.47
5.13 | ESP |  |  | Kg | 125257.14 | 120894.4233 | 0 | 120894.4233 | 4362.7167
5.14 | CBD Tank |  |  | Kg | 724.34 | 724.34 | 0 | 724.34 | 0 | Completed
5.15 | LP Dosing |  |  | Kg | 1050 | 0 | 0 | 0 | 1050
5.17 | HP Dosing |  |  | Kg | 1250 | 1250 | 0 | 1250 | 0 | Completed
| Sub Total |  |  | Kg | 252961.955 | 213168.7983 | 9311.95 | 222480.7483 | 30481.2067
6 | PIPING | [7 empty] | 0
6.1 | Intergral Piping |  |  | Kg | 14916.49 | 14916.49 | 0 | 14916.49 | 0 | Completed
6.2 | Integral piping support |  |  | Kg | 1701.8705 | 1701.8705 | 0 | 1701.8705 | 0 | Completed
6.3 | Cooling water piping |  |  | Kg | 1059.98 | 0 | 0 | 0 | 1059.98
6.4 | Boiler House Piping |  |  | Kg | 22180.61 | 410 | 0 | 410 | 21770.61
6.5 | Boiler House Piping supports |  |  | Kg | 10932.7295 | 0 | 0 | 0 | 10932.7295
| Sub Total |  |  | Kg | 50791.68 | 4747.25 | 0 | 17028.3605 | 33763.3195
7 | NDT |  |  | nos | 120 | 120 | 0 | 120 | 0 | Completed
8 | REFRACTORY |  |  | kg | 37000 | 1950 | 0 | 1950 | 35050
9 | INSULATION |  |  | SQM | 3820 | 0 | 0 | 0 | 3820
| Boiler Total |  |  |  | 620748.3865 | 460317.5373 | 9311.95 | 481910.5978 | 138837.7887
11 | Coal Handling system
11.1 | BC-1 |  |  | Kg | 32546.83 | 28777.26 | 0 | 28777.26 | 3769.57
11.2 | BC-2 |  |  | Kg | 5868.26 | 2935.6 | 0 | 2935.6 | 2932.66
11.3 | BC-3 and RBC |  |  | Kg | 20573.63 | 9436.67 | 210 | 9646.67 | 10926.96
| FHS Total |  |  |  | 58988.72 | 41149.53 | 210 | 41359.53 | 17629.19
12 | Ash handling system |  |  | Kg | 43829 | 35086 | 180 | 35266 | 8563
| AHS Total |  |  | Kg | 43829 | 35086 | 180 | 35266 | 8563
| Grand Total |  |  | KG | 723566.1065 | 536553.0673 | 9701.95 | 558536.1278 | 165029.9787 |  | 0
| ISGEC STAFF |  |  |  |  | Manpower Samarth Engineering |  |  |  | Aditya insulation
| Category |  |  | Quantity |  | Category |  | Quantity |  | Category | Quantity
| Site Incharge |  |  | 1 |  | Site Incharge |  | 1 |  | Site Incharge | 1
| Erection Engineer |  |  | 1 |  | Engineer |  | 1 |  | Welder | 1
| QC Engineer |  |  | 1 |  | QC Engineer |  | 1 |  | Scaffolder | 4
| Electrical Engineer |  |  | 1 |  | Electrician |  | 1 |  | Helper | 1
| Instrumentation Engineer |  |  | 1 |  | Supervisors |  | 1 |  | Welder | 1
| EHS officer |  |  | 1 |  | Safety Officer |  | 1 |  | Total | 8
| Store Keeper |  |  | 1 |  | Fitter |  | 8
| CHS erection engineer |  |  | 1 |  | Mill Wright |  | 0 |  | Saarc Refractory
| Total |  |  | 7 |  | IBR welder |  | 0 |  | Site Incharge | 1
[6 empty] | Welder |  | 8 |  | Scaffolder | 2
[6 empty] | Gas Cutter |  | 2 |  | Carpenter | 1
[6 empty] | Grinder |  | 2 |  | Mason | 1
[6 empty] | Foreman |  | 1 |  | Helper | 3
[6 empty] | Rigger |  | 14 |  | Total | 8
[6 empty] | Helper |  | 10
[6 empty] | Kalasi |  | 5 |  | Star Instruments
[6 empty] | Stores |  | 1 |  | Category | Quantity
[6 empty] | Hydra operator |  | 1 |  | Supervisor | 1
[6 empty] | Crane operator + assistant |  | 2 |  | Welder | 2
[6 empty] | Total |  | 60 |  | fitter | 1
[10 empty] | Technican | 1
[10 empty] | Khalasi | 1
[10 empty] | Helper | 1
[10 empty] | Total | 7
83