## CCT
DEEPAK FERTILISERS & PERTOCHEMICALS COPORATION LIMITED
ISGEC HEAVY ENGINEERING LIMITED
PROJECT :NITRIC ACID COMPLEX - Rev-03 (Updated)
PARENT BUNDLE:40 TPH AFBC BOILER
PHASE:Construction
SL.NO | DESCRIPTION OF ITEM |  |  | UOM | SCOPE | Progress |  |  |  | Remarks
|  | Start | End |  |  | Till Previous day | Today | Cumm | Balance
1.0 | STRUCTURE
1.1 | Columns | NA | NA | Kg | 25152.73 | 25152.73 | 0 | 25152.73 | 0 | Completed
1.2 | Canopy Strurcture | 2018-08-22 | 2018-09-28 | Kg | 20777.92 | 18252.73 | 0 | 18252.73 | 2525.19
1.3 | Beams and bracing | 2018-08-10 | 2018-09-20 | Kg | 56383.81 | 55907.38 | 0 | 55907.38 | 476.43
1.4 | Grating, Staircase, chequred Plate, Hand Rail | 2018-08-20 | 2018-09-25 | Kg | 15925.34 | 10935.569 | 0 | 10935.569 | 4989.771
| Sub Total |  |  | Kg | 118239.8 | 110248.409 | 0 | 110248.409 | 7991.391
2.0 | BOILER PRESSURE PARTS
2.1 | Steam drum | 2018-08-03 | 2018-09-18 | Kg | 11303.18 | 10391.09 | 0 | 10391.09 | 912.09
2.2 | Front Water Wall Panels | 2018-06-20 | 2018-08-20 | Kg | 6798.83 | 6798.83 | 0 | 6798.83 | 0 | Completed
2.3 | Rear Water Wall Panels | 2018-06-25 | 2018-08-24 | Kg | 4671.89 | 4671.89 | 0 | 4671.89 | 0 | Completed
2.4 | RHS Water wall Panels | 2018-06-30 | 2018-08-26 | Kg | 5722.54 | 5722.54 | 0 | 5722.54 | 0 | Completed
2.5 | LHS Water Wall Panels | 2018-07-12 | 2018-08-22 | Kg | 5761.1 | 5761.1 | 0 | 5761.1 | 0 | Completed
2.6 | Convective Super Heater Coil | 2018-07-10 | 2018-09-18 | Kg | 13627.34 | 13393.46 | 0 | 13393.46 | 233.88
2.7 | Radiant Super Heater Coil | NA | NA | Kg | 8355.41 | 8355.41 | 0 | 8355.41 | 0 | Completed
2.8 | Economiser Coils | NA | NA | Kg | 21996.84 | 21996.84 | 0 | 21996.84 | 0 | Completed
2.9 | Bed Coil | NA | NA | Kg | 10837.75 | 10837.75 | 0 | 10837.75 | 0 | Completed
| Sub Total |  |  | Kg | 89074.88 | 87928.91 | 0 | 87928.91 | 1145.97
3 | BUCK STAY and seismic supports | [7 empty] | 0
3.1 | Buckstay | 2018-08-02 | 2018-09-18 | Kg | 5188.28 | 4900.8 | 0 | 4900.8 | 287.48
3.2 | Seismic support | NA | NA | Kg | 747.94 | 747.94 | 0 | 747.94 | 0 | Completed
| Sub Total |  |  | Kg | 5936.22 | 5648.74 | 0 | 5648.74 | 287.48
4 | DUCTING AND CASING
4.1 | FD duct | 2018-08-25 | 2018-10-02 | Kg | 9947.644 | 3250.49 | 0 | 3250.49 | 6697.154
4.2 | PA duct | 2018-08-27 | 2018-09-25 | Kg | 3142.492 | 2189.62 | 0 | 2189.62 | 952.872
4.3 | SA duct | 2018-08-20 | 2018-09-25 | Kg | 2146.35 | 888.09 | 0 | 888.09 | 1258.26
4.4 | FG duct | 2018-08-22 | 2018-09-30 | Kg | 21845.6805 | 6991.87 | 789.35 | 7781.22 | 14064.4605
4.5 | Air Box | 2018-08-10 | 2018-09-15 | Kg | 12959.84 | 12830.73 | 0 | 12830.73 | 129.11
4.7 | APH Casing | 2018-08-12 | 2018-09-18 | Kg | 2269.895 | 2081.24 | 0 | 2081.24 | 188.655
4.8 | Economiser casing | 2018-08-27 | 2018-09-18 | Kg | 4048.025 | 3219.12 | 0 | 3219.12 | 828.905
4.9 | Furnace bottom Sealing | 2018-09-09 | 2018-09-20 | Kg | 2215.37 | 121 | 0 | 121 | 2094.37
4.1 | Cover plates and doors | 2018-08-18 | 2018-09-20 | Kg | 2357.15 | 2092.79 | 0 | 2092.79 | 264.36
4.11 | Hopper | 2018-08-20 | 2018-09-20 | Kg | 3613.065 | 3386.83 | 0 | 3386.83 | 226.235
4.12 | Foundation bolts | 2018-08-14 | 2008-09-25 | Kg | 2198.34 | 1705.61 | 0 | 1705.61 | 492.73
| Sub Total |  |  | Kg | 66743.8515 | 38757.39 | 789.35 | 39546.74 | 27197.1115
5 | EQUIPMENT
5.1 | De-aerator | 2018-07-15 | 2018-09-17 | Kg | 10050.5 | 8474.48 | 779.87 | 9254.35 | 796.15
5.2 | Air heater | NA | NA | Kg | 15809.02 | 15809.02 | 0 | 15809.02 | 0 | Completed
5.3 | FD Fan | 2018-09-11 | 2018-09-18 | Kg | 4340 | 4098 | 0 | 4098 | 242
5.4 | ID Fan | 2018-09-13 | 2018-09-18 | Kg | 5060 | 4759 | 0 | 4759 | 301
5.5 | PA Fan | 2018-09-14 | 2018-09-16 | Kg | 2300 | 2118 | 0 | 2118 | 182
5.6 | BFP with Motor | 2018-09-13 | 2018-09-30 | Kg | 13930 | 0 | 0 | 0 | 13930
5.7 | Feeders | 2018-08-22 | 2018-09-18 | Kg | 8735 | 8235 | 0 | 8235 | 500
5.8 | Coal Bunker 1 | 2018-08-12 | 2018-08-30 | Kg | 19725.07 | 19725.07 | 0 | 19725.07 | 0
5.9 | Coal Bunker 2 | 2018-08-14 | 2018-08-30 | Kg | 16941.28 | 16941.28 | 0 | 16941.28 | 0
5.1 | Lime stone Bunker | 2018-08-14 | 2018-08-30 | Kg | 10571.88 | 10571.88 | 0 | 10571.88 | 0
5.11 | Bed Material Bunker | 2018-08-16 | 2018-09-05 | Kg | 3955.535 | 3955.535 | 0 | 3955.535 | 0
5.12 | Fuel feeding system' | 2018-09-15 | 2018-10-01 | Kg | 13262.19 | 9372.92 | 0 | 9372.92 | 3889.27
5.13 | ESP | 2018-06-10 | 2018-09-20 | Kg | 125257.14 | 120894.4233 | 0 | 120894.4233 | 4362.7167
5.14 | CBD Tank | NA | NA | Kg | 724.34 | 724.34 | 0 | 724.34 | 0 | Completed
5.15 | LP Dosing | 2018-09-27 | 2018-09-30 | Kg | 1050 | 0 | 0 | 0 | 1050
5.17 | HP Dosing | 2018-09-05 | 2018-09-08 | Kg | 1250 | 1250 | 0 | 1250 | 0 | Completed
| Sub Total |  |  | Kg | 252961.955 | 226928.9483 | 779.87 | 227708.8183 | 25253.1367
6 | PIPING | [7 empty] | 0
6.1 | Intergral Piping | 2018-07-10 | 2018-08-30 | Kg | 14916.49 | 14916.49 | 0 | 14916.49 | 0 | Completed
6.2 | Integral piping support | 2018-07-10 | 2018-08-30 | Kg | 1701.8705 | 1701.8705 | 0 | 1701.8705 | 0 | Completed
6.3 | Cooling water piping | 2018-09-10 | 2018-09-30 | Kg | 1059.98 | 0 | 0 | 0 | 1059.98
6.4 | Boiler House Piping | 2018-09-05 | 2018-09-30 | Kg | 22180.61 | 410 | 0 | 410 | 21770.61
6.5 | Boiler House Piping supports | 2018-09-15 | 2018-10-05 | Kg | 10932.7295 | 0 | 0 | 0 | 10932.7295
| Sub Total |  |  | Kg | 50791.68 | 4747.25 | 0 | 17028.3605 | 33763.3195
7 | NDT
7.1 | NDT | 2018-08-20 | 2018-09-08 | nos | 120 | 120 | 0 | 120 | 0 | Completed
8 | REFRACTORY
8.1 | REFRACTORY | 2018-08-26 | 2018-09-18 | kg | 37000 | 2400 | 600 | 3000 | 34000
9 | INSULATION
9.1 | INSULATION | 2018-09-15 | 2018-10-10 | SQM | 3820 | 0 | 0 | 0 | 3820
| Boiler Total |  |  |  | 620748.3865 | 476659.6473 | 2169.22 | 491109.9778 | 129638.4087
11 | Coal Handling system
11.1 | BC-1 | 2018-08-20 | 2018-09-15 | Kg | 32546.83 | 28777.26 | 0 | 28777.26 | 3769.57
11.2 | BC-2 | 2018-08-22 | 2018-09-18 | Kg | 5868.26 | 2935.6 | 0 | 2935.6 | 2932.66
11.3 | BC-3 and RBC | 2018-08-25 | 2018-09-27 | Kg | 20573.63 | 9646.67 | 1111.4 | 10758.07 | 9815.56
| FHS Total |  |  |  | 58988.72 | 41359.53 | 1111.4 | 42470.93 | 16517.79
17 | Ash handling system
17.1 | Ash handling system | 2018-07-15 | 2018-09-25 | Kg | 43829 | 35266 | 0 | 35266 | 8563
| AHS Total |  |  | Kg | 0 | 0 | 0 | 0 | 0
12 | INSTRUMENTATION
12.1 | Pressure Transmitter | 2018-09-15 | 2018-09-30 | Nos. | 15 | 0 | 0 | 0 | 15
12.2 | Differential Pressure Transmitter | 2018-09-15 | 2018-09-30 | Nos. | 26 | 0 | 0 | 0 | 26
12.3 | Level Switch / Transmitter | 2018-09-15 | 2018-09-30 | Nos. | 18 | 0 | 0 | 0 | 18
12.4 | Temperature Transmitter | 2018-09-15 | 2018-09-30 | Nos. | 8 | 0 | 0 | 0 | 8
12.5 | Pressure Switch | 2018-09-10 | 2018-09-28 | Nos. | 22 | 0 |  |  | 22
12.6 | Limit Switch (InBuilt with Actuator, CV, Damper etc.) | 2018-09-20 | 2018-10-02 | Nos. | 24 | 0 | 0 | 0 | 24
12.7 | Junction box/ PDB/ hooter along with cable gland | 2018-09-01 | 2018-09-15 | Nos. | 41 | 0 | 0 | 0 | 41
12.8 | Cable Tray | 2018-09-01 | 2018-09-18 | Mtr. | 1800 | 0 | 0 | 0 | 1800
12.9 | Cables | 2018-09-05 | 2018-09-30 | Mtr. | 11480 | 0 | 0 | 0 | 11480
12.1 | Level Gauges | 2018-09-10 | 2018-09-25 | Nos. | 8 | 0 | 0 | 0 | 8
12.11 | Pressure Gauges | 2018-09-10 | 2018-09-25 | Nos. | 57 | 0 | 0 | 0 | 57
12.12 | Temperature Gauges | 2018-09-10 | 2018-09-25 | Nos. | 8 | 0 | 0 | 0 | 8
12.13 | Temperature Elements | 2018-09-10 | 2018-09-28 | Nos. | 71 | 0 | 0 | 0 | 71
12.14 | Flow Elements | 2018-09-10 | 2018-09-28 |  | 4 | 0 | 0 | 0 | 4
12.15 | Control valves/ dampers | 2018-09-12 | 2018-09-30 | Nos. | 19 | 0 |  | 0 | 19
12.16 | On- Off valve / Actuator | 2018-09-12 | 2018-09-30 | Nos. | 29 | 0 | 0 | 0 | 29
12.17 | Switches | 2018-09-05 | 2018-09-28 | Nos. | 36 | 0 | 0 | 0 | 36
12.18 | UPS SYSTEM | 2018-09-20 | 2018-09-24 | Nos. | 1 | 0 | 0 | 0 | 1
12.19 | DCS SYSTEM | 2018-09-15 | 2018-09-30 | Nos. | 1 | 0 | 0 | 0 | 1
12.2 | SWAS System | 2018-09-20 | 2018-09-30 | Nos. | 1 | 0 | 1 | 1 | 0
12.21 | O2 Analyzer (SET) | 2018-09-25 | 2018-10-02 | Nos. | 1 | 0 | 0 | 0 | 1
12.22 | AHS Pneumatic Panels | 2018-09-05 | 2018-09-20 | Nos. | 6 | 0 | 0 | 0 | 6
12.23 | Air compressor system | 2018-09-12 | 2018-09-20 | Nos. | 2 | 0 |  | 0 | 2
12.24 | Metal Detector | 2018-09-20 | 2018-09-22 | Nos. | 1 | 0 | 0 | 0 | 1
12.25 | Magnetic Seperator | 2018-09-28 | 2018-09-30 | Nos. | 1 | 0 | 0 | 0 | 1
13 | ELECTRICAL | [7 empty] | 0
13.1 | Transformer forESP | 2018-09-15 | 2018-09-25 | Nos. | 4 | 0 | 4 | 4 | 0
13.2 | MCC Panels | 2018-09-20 | 2018-09-25 | Nos. | 2 | 0 | 0 | 0 | 2
13.3 | VFD Panels | 2018-09-18 | 2018-09-22 | Nos. | 5 | 0 | 0 | 0 | 5
13.4 | TRCC Panels | 2018-09-20 | 2018-09-22 | Nos. | 4 | 0 | 4 | 4 | 0
13.5 | Installation of LCS/JB/LPBS | 2018-09-02 | 2018-09-22 | Nos. | 74 | 0 | 0 | 0 | 74
13.6 | Erection of cable tray | 2018-09-01 | 2018-09-20 | Kg | 1600 | 53 | 0 | 53 | 1547
13.7 | Erection of cable tray bend | 2018-09-10 | 2018-09-20 | Nos. | 255 | 0 | 0 | 0 | 255
13.8 | Earthing strip | 2018-09-01 | 2018-09-15 | Kg | 2500 | 0 | 0 | 0 | 2500
13.9 | Steel structure support | 2018-09-01 | 2018-09-30 | Kg | 4960 | 1400 | 0 | 1400 | 3560
13.1 | Laying of Power & Control cables | 2018-09-05 | 2001-10-03 | Mtrs. | 17020 | 0 |  | 0 | 17020
13.11 | Glanding & Termination of LV Cables (Panel gland Both Side) | 2018-09-20 | 2018-10-05 | nos. | 2706 | 0 | 0 | 0 | 2706
14 | TRIAL RUN
14.1 | Trial run of BFP Motor | 2018-10-06 | 2018-10-06 |  |  | NA | NA | NA |  | Single Activity
14.2 | Trail run of BFP Pump 1 & 2 with all logics | 2018-10-06 | 2018-10-06 |  |  | NA | NA | NA |  | Single Activity
14.3 | Trial run of ID Fan with all logics | 2018-10-07 | 2018-10-07 |  |  | NA | NA | NA |  | Single Activity
14.4 | Trial run of Air compressors | 2018-10-08 | 2018-10-08 |  |  | NA | NA | NA |  | Single Activity
14.5 | Trial run of Ash Conveying system | 2018-10-08 | 2018-10-08 |  |  | NA | NA | NA |  | Single Activity
14.6 | Trail run of FHS | 2018-10-09 | 2018-10-11 |  |  | NA | NA | NA |  | Single Activity
14.7 | Trial run of FD Fan with all logics | 2018-10-06 | 2018-10-07 |  |  | NA | NA | NA |  | Single Activity
14.8 | Trial run of PA Fan with all logics | 2018-10-05 | 2018-10-05 |  |  | NA | NA | NA |  | Single Activity
14.9 | Trial run of CHP Motors | 2018-10-05 | 2018-10-07 |  |  | NA | NA | NA |  | Single Activity
14.1 | Integrated Trial run BC - 1, BC - 2, BC - 3 | 2018-10-10 | 2018-10-11 |  |  | NA | NA | NA |  | Single Activity
14.11 | Receipt of Bed Material | 2018-10-05 | 2018-10-05 |  |  | NA | NA | NA |  | Single Activity
14.12 | Receipt of Coal | 2018-10-06 | 2018-10-06 |  |  | NA | NA | NA |  | Single Activity
15 | AVAILABILITY OF COMMISSIONING MATERIAL
15.1 | Receipt of Lime stone | 2018-10-06 | 2018-10-06 |  |  | NA | NA | NA | NA
15.2 | Availability of DM Water at terminal Point | 408615 | 2018-10-01 |  |  | NA | NA | NA | NA
15.3 | Availability of Coal | 2018-09-30 | 2018-09-30 |  |  | NA | NA | NA | NA
15.4 | Availability of Charcoal & Wood | 2018-09-30 | 2018-09-30 |  |  | NA | NA | NA | NA
15.5 | Conducting DP Test for Furnace | 2018-10-06 | 2018-10-06 |  |  | NA | NA | NA | NA
15.6 | Bed material Filling | 2018-10-07 | 2018-10-08 |  |  | NA | NA | NA | NA
16 | PRE-COMMISSIONING
16.1 | Filling of coal bunker | 2018-10-10 | 2018-10-10 |  |  | NA | NA | NA | NA
16.2 | Filling of Lime stone | 2018-10-11 | 2018-10-11 |  |  | NA | NA | NA | NA
16.3 | Conducting DP Test after Bed material filling | 2018-10-09 | 2018-10-10 |  |  | NA | NA | NA | NA
16.4 | Charging of wood pieces | 2018-10-10 | 2018-10-10 |  |  | NA | NA | NA | NA
16.5 | Charging of chemicals and recirculation start for ABO | 2018-10-11 | 2018-10-11 |  |  | NA | NA | NA | NA
16.6 | Initial firing for RDO | 2018-10-12 | 2018-10-12 |  |  | NA | NA | NA | NA
16.7 | RDO Activity | 2018-10-13 | 2018-10-15 |  |  | NA | NA | NA | NA
16.8 | Blow down and rinsing | 2018-10-16 | 2018-10-16 |  |  | NA | NA | NA | NA
16.9 | Refractory inspection | 2018-10-17 | 2018-10-17 |  |  | NA | NA | NA | NA
16.1 | Installation of Steam drum internals. | 2018-10-18 | 2018-10-18 |  |  | NA | NA | NA | NA
16.11 | Replacing the bed material with new material | 2018-10-18 | 2018-10-18 |  |  | NA | NA | NA | NA
16.12 | Steam Out | 2018-10-19 | 2018-10-20 |  |  | NA | NA | NA | NA
| Grand Total |  |  | KG | 679737.1065 | 518019.1773 | 3280.62 | 533580.9078 | 146156.1987
| ISGEC STAFF | [6 empty] | Manpower Samarth Engineering |  |  | Aditya insulation
| Category |  |  | Quantity |  |  |  | Category |  | Quantity | Category | Quantity
| Site Incharge |  |  | 1 |  |  |  | Site Incharge |  | 1 | Site Incharge | 1
| Erection Engineer |  |  | 1 |  |  |  | Engineer |  | 2 | Welder | 1
| QC Engineer |  |  | 1 |  |  |  | QC Engineer |  | 0 | Scaffolder | 4
| Electrical Engineer |  |  | 1 |  |  |  | Electrician |  | 1 | Helper | 2
| Instrumentation Engineer |  |  | 1 |  |  |  | Supervisors |  | 1 | Welder | 1
| EHS officer |  |  | 1 |  |  |  | Safety Officer |  | 1 | Total | 9
| Store Keeper |  |  | 1 |  |  |  | Fitter |  | 9
| CHS erection engineer |  |  | 1 |  |  |  | Mill Wright |  | 0 | Saarc Refractory
| Total |  |  | 7 |  |  |  | IBR welder |  | 1 | Site Incharge | 1
[8 empty] | Welder |  | 11 | Scaffolder | 2
[8 empty] | Gas Cutter |  | 2 | Carpenter | 1
[8 empty] | Grinder |  | 2 | Mason | 1
[8 empty] | Foreman |  | 1 | Helper | 3
[8 empty] | Rigger |  | 14 | Total | 8
[8 empty] | Helper |  | 12
[8 empty] | Kalasi |  | 5 | Star Instruments
[8 empty] | Stores |  | 1 | Category | Quantity
[8 empty] | Hydra operator |  | 1 | Supervisor | 1
[8 empty] | Crane operator + assistant |  | 2 | Welder | 2
[8 empty] | Total |  | 67 | fitter | 1
[11 empty] | Technican | 1
[11 empty] | Khalasi | 1
[11 empty] | Helper | 1
[11 empty] | Total | 7
91