## Man power
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ.
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE: 19.06.2018
STRUCTURE WISE DEPLOYMENT
Sr.No. | CATEGORY | UNIT | SUB STATION | Control Room | Vam unit | AMMONIA tanks | AMMONIA Compressor | AMMONIA TANKER LOADING | WNA STORAGE TANK | CAN STORAGE TANK | SNA STORAGE TANK | DM PLANT | COOLING TOWERS | RWTP | TG Building | BOILER | WNA & SNA loading bay | AMMONIA Scrubber | Caustic & Sulphuric Storage tank | TOTAL DEPLOYMENT IN NO.
1 | Unskiled labour | no | 4 | 2 |  | 7 | 2 |  | 18 | 20 | 4 |  | 10 | 1 | 27 |  |  |  |  | 95 | 97
2 | Mason | no | 6 |  |  | 1 | 1 |  | 2 | 4 | 2 | 1 | 4 | 1 | 8 | 1 |  |  | 2 | 33
3 | Carpenter+barbender+ Helper | no |  | 0 |  |  | 2 | 0 | 2 | 2 |  |  | 4 |  | 28 | 0 |  | 0 | 0 | 38
4 | Welder/Fitter/Riger | no | 0 | 0 |  |  | 0 |  |  | 2 | 2 |  | 0 | 0 | 25 | 0 |  |  | 0 | 29
5 | JCB Operator | no | 1 | 0 | 0 | 1 |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 1 |  | 0 | 3
6 | Tractor drivers | no | 1 | 0 | 0 |  | 0 |  |  | 0 |  |  | 1 |  | 1 | 0 | 1 |  |  | 4
7 | TM | no | 1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 1 |  |  | 0 | 2
8 | Concrete pump | no | 1 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 1

## work report
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE:19.06.2018
PROGRESS : 18.06.2018
WORK REPORT
Sr.No. | ITEM | UNIT | QUANTITIES |  |  |  | TODAY PLANING | REMAKS
|  |  | TOTAL SCOPE | PREVIOUS PROGRESS | TODAY PROGRESS | TOTAL PROGRESS
1 | SUB STATION
a | Footing excavation | Nos. | 52 | 52 |  | 52 | 0
b | PCC in footings | Nos. | 52 | 52 |  | 52 | 0
c | RCC footings | Nos. | 52 | 52 |  | 52 | 0
d | Colums up to plinth | Nos. | 56 | 56 |  | 56 | 0
e | Columns above plinth | Nos. | 56 | 56 |  | 56
f | Plinth beam | Nos. | 41 | 41 |  | 41
g | Soling under floor | Cum. | 235 | 235 |  | 235
h | PCC under floor | Cum. | 82.625 | 82.63 | 0 | 82.63
i | Slab +3.40m lvl | cum | 245 | 245 |  | 245 | 0
j | Column Above Slab 1st lift | Nos. | 48 | 48 |  | 48
k | Column Above Slab 2nd lift | Nos. | 48 | 48 |  | 48
l | Plaster | sqm |  | 5118 | 32 | 5150
m | Lintel Beam | Cum | 24 | 23.99 |  | 23.99
n | Slab +7.900m lvl | Cum. | 255 | 255 |  | 255
o | Transformer foundation P.C.C. | no. | 4 | 4 |  | 4
p | Transformer foundation R.C.C. | no. | 4 | 4 |  | 4
q | Pedestal 1st lift | no. | 8 | 8 |  | 8
r | Pedestal 2nd lift | no. | 8 | 8 |  | 8
s | Pedestal top Lift with Insert Plate | no. | 8 | 8 |  | 8
t | Transformer Beam | No |  | 6 |  | 6
u | Trimix flooring | sqm |  | 1080 |  | 1080
v | IPS for Flooring | Cum. |  | 30 |  | 30
w | Parapet | Cum. |  | 4 |  | 4
X | Transformer Floor & Wall | Cum. |  | 4 | 2 | 6
Y | Transformer Curb Wall | Cum. |  | 2.25 |  | 2.25
z | Window Fixing | Nos. |  | 6 | 2 | 6
A1 | Grade Slab in transformer | Cum |  | 4 |  | 4
2 | CONTROL ROOM
a | Footing excavation | Nos. | 40 | 40 | 0 | 40
b | PCC in footings | Nos. | 40 | 40 | 0 | 40
c | RCC footings | Nos. | 40 | 40 | 0 | 40 | 0
d | Colums up to plinth | Nos. | 40 | 40 | 0 | 40 | 0
e | Plinth beam | Nos. | 62 | 62 |  | 62
f | Columns above plinth | Nos. | 40 | 40 |  | 40
g | Brick work | Cum. |  | 76.7 |  | 76.7
h | Lintel Beam | Rmt |  | 86 |  | 86
i | Slab | Cum. |  | 138 |  | 138 |  | Completed on 09.03.2018
j | Strong room wall 1 nd lift | no. | 1 | 1 |  | 1
k | Strong room wall 2 nd lift | no. | 1 | 1 |  | 1
l | Strong room Slab | Cum. | 15.5 | 15.5 |  | 15.5 |  | Completed on 03.04.2018
m | Grade Slab | Cum. |  | 67.5 |  | 67.5
n | Plaster | Sqm. |  | 1870 |  | 1870
o | Window Fixing | no |  | 20 |  | 20
p | IPS for Flooring | Cum |  | 3 |  | 3
3 | AMMONIA STORAGE TANK
a | Footing excavation | Nos. | 10 | 10 |  | 10 | 0 | Completed on 05.02.18
b | PCC in footings | Nos. | 10 | 10 |  | 10 | 0
c | RCC footings | Nos. | 10 | 10 |  | 10
d | Pedestal 1st lift | Nos. | 10 | 10 |  | 10
e | Pedestal 2nd lift | Nos. | 10 | 10 |  | 10
f | Filling for grade slab | cum |  | 520 |  | 520
g | Dyke Wall P.C.C. | Rmt |  | 138.5 |  | 138.5
h | Dyke Wall raft | Rmt |  | 126.5 |  | 126.5
i | Dyke Wall | Rmt |  | 126.5 |  | 126.5
J | Soling | Sqm |  | 508 |  | 508
k | Floor P.C.C. | Cum |  | 19 |  | 19
I | Drain P.C.C. | Rmt |  | 36 |  | 36
J | Drain Raft | Rmt |  | 11 |  | 11
4 | WNA TANK
a | Tank excavation | Cum. | 1100 | 875 | 0 | 875 | 0
b | PCC in TANK | Nos. | 2 | 2 | 0 | 2 | 0
C | Tank raft | Nos. | 2 | 2 | 0 | 2 | 0
d | Tank- Wall | Nos. | 2 | 2 | 0 | 2
e | PCC in Footing | Nos. | 4 | 4 | 0 | 4
f | RCC footings | Nos. | 4 | 4 |  | 4
g | Column | Nos. | 4 | 4 |  | 4
h | Filling in Tank | Nos. | 2 | 2 |  | 2
i | PCC on top | Nos. | 2 | 2 |  | 2
j | Tank top | Nos. | 2 | 2 |  | 2 | 0
k | Dyke wall PCC | Rmt |  | 110 |  | 110
l | Dyke wall Raft | Rmt |  | 110 |  | 110
m | Dyke wall RCC 1st lift | Rmt |  | 110 |  | 110
n | Dyke wall RCC 2nd lift | Rmt |  | 110 |  | 110
o | Dyke wall RCC 3rd lift | Rmt |  | 0
5 | VAM UNIT
a | Footing excavation | no | 10 | 10 | 0 | 10 | 0 | 22.1.18
b | PCC in footings | no | 10 | 10 |  | 10 | 0
c | RCC footings | no | 10 | 10 |  | 10 | 0
d | Colums up to plinth | no | 10 | 10 |  | 10 | 0
e | Columns with bolt | no | 10 | 10 |  | 10 | 0
f | Soling under floor | cum | 37 | 37 |  | 37 | 0
g | PCC under floor | cum | 20 | 20 |  | 20 | 0
h | Dyke wall | rmt | 51 | 51 |  | 51
i | Grade slab | Cum | 35 | 34.5 |  | 34.5
j | Foundations | cum | 15 | 15 |  | 15
6 | CAN storage tank
a | Raft excavation-4 nos | Nos. | 4 | 3 | 0 | 3 | 0
b | Raft PCC | Nos. | 4 | 3 | 0 | 3
c | Raft RCC | Nos. | 4 | 3 | 0 | 3 | 0
d | Raft Pedestal 1st lift | Nos. | 32 | 24 |  | 24
e | Raft Pedestal 2nd lift | Nos. | 32 | 24 |  | 24
f | Raft Pedestal 3rd lift | Nos. | 32 | 7 |  | 7
g | Footing excavation | Nos. | 28 | 28 | 0 | 28
h | Footing P.C.C. | Nos. | 28 | 28 |  | 28
i | Footing R.C.C. | Nos. | 28 | 28 |  | 28
j | Pedestal 1st lift | Nos. | 28 | 28 |  | 28
k | Pedestal 2nd Lift | Nos. | 28 | 28 |  | 28
l | Soling | Sqm |  | 212 |  | 212
j | CAN Flooring | Cum |  | 10 |  | 10
k | Dyke Wall P.C.C. | Rmt |  | 22 |  | 22
L | Dyke Wall R.C.C. raft | RMT |  | 22 |  | 22
M | Dyke Wall | RMT |  | 22 |  | 22
7 | SNA storage tank
a | Tank excavation | no | 2 | 2 |  | 2 | 0 | Completed on 1.1.18 of 1st Tank & 2 nd tank on 08.05.2017
b | PCC in TANK | no | 2 | 2 |  | 2 | 0
c | Tank raft | no | 2 | 2 |  | 2 | 0
d | Tank Wall 1st lift | no | 2 | 2 | 0 | 2 | 0
e | Tank Wall 2nd lift | no | 2 | 2 |  | 2 | 0
f | Filling in Tank | cum |  | 32 | 0 | 32 | 0
g | PCC at top | cum |  | 2 | 0 | 2 | 0
h | Tank top | cum |  | 2 | 0 | 2 | 0
i | Bitumastic pad | sqm |  | 20 | 0 | 20
j | Footing R.C.C. | No. |  | 4 |  | 4
k | Pedestal | No. |  | 2 |  | 2
L | Dyke Wall P.C.C. | Rmt |  |  | 25 | 25
8 | Air Compressor
a | Footing excavation | no | 10 | 10 | 0 | 10 | 0 | Completed on 05.02.2018
b | PCC in footings | no | 10 | 10 | 0 | 10 | 0
c | RCC footings | no | 10 | 10 | 0 | 10 | 0
d | Colums up to plinth | no | 10 | 10 | 0 | 10 | 0
e | Columns with bolt | no | 10 | 10 | 0 | 10 | 0
f | Soling under floor | sqm | 136.5 | 136.5 | 0 | 136.5
g | P.C.C. above soling | Cum | 12.857 | 12.86 |  | 12.86
h | Dyke wall | rmt | 38.18 | 38.18 |  | 38.18
i | Grade slab | Cum | 18.611 | 18.611 |  | 18.611
j | Ramp | Cum | 4.777 | 4.78 |  | 4.78
k | Foundations | Cum | 42.252 | 42.25 |  | 42.25
9 | D M Plant
a | Footing excavation | no | 10 | 10 | 0 | 10 | 0
b | PCC in footings | no | 10 | 10 | 0 | 10 | 0
c | RCC footings | no | 10 | 10 | 0 | 10 | 0
d | Columns up to plinth | no | 10 | 10 | 0 | 10 | 0
e | Column above plinth 1st lift | no | 6 | 6 |  | 6
f | Column above plinth 2nd lift | no | 6 | 6 |  | 6
g | Columns with bolt | no | 4 | 4 | 0 | 4 | 0
h | DM tank PCC | no | 1 | 1 | 0 | 1 | 0
i | DM tank RCC raft | no | 1 | 1 | 0 | 1
j | DM tank wall 1st lift | no | 1 | 1 |  | 1
k | DM tank wall /Final lift | no | 1 | 1 | 0 | 1
l | sludge pit wall | Cum |  | 8.5 |  | 8.5
m | R.C.C. Floor | Cum |  | 19 |  | 19
n | Foundations | no. |  | 27 |  | 27 |  | Completed on 05.02.2018
o | Cerb Wall | Rmt. | 79.2 | 79.2 |  | 79.2
p | Slab of Panel Room | Cum. | 8 | 8 |  | 8 |  | Completed on 21.03.2018
10 | Cooling Tower
a | Footing excavation | no | 35 | 35 | 0 | 35 | 0
b | PCC in footings | no | 35 | 35 | 0 | 35
c | RCC footings | no | 35 | 35 |  | 35
d | Columns pedestal | no | 35 | 35 |  | 35
e | Plinth beam P.C.C. | Cum |  | 9.5 | 0 | 9.5
f | Drain P.C.C. | rmt |  | 83 |  | 83
g | Drain Raft | Rmt |  | 83 |  | 83
h | Drain Wall | Rmt |  | 57 |  | 57
i | Grade slab P.C.C. outside area | Cum |  | 16 |  | 16
j | Grade Slab R.C.C. outside area | Cum |  | 21 |  | 21
k | Grade Slab pcc | Cum | 45 | 45 |  | 45
l | Grade slab RCC | cum | 91.5 | 92.35 |  | 92.35
m | Sump wall 1st lift | cum | 40 | 40 | 0 | 40
n | Sump wall 2nd lift | Cum | 20 | 19.5 |  | 19.5
o | Sump Slab | Cum | 18.5 | 17.5 |  | 17.5
p | Column | no. | 126 | 126 |  | 126
q | Basin wall 1st lift | cum | 32 | 32 |  | 32
r | Basin wall 2nd lift | cum | 32 | 32 |  | 32
s | Pump Foundation P.C.C. | No. | 10 | 8 |  | 8
t | Pump Foundation R.C.C. 1st Lift | No. | 10 | 8 |  | 8
u | Pump Foundation R.C.C. final Lift | no | 10 | 8 |  | 8
v | Sleeper | No. |  | 5 |  | 5
w | Column Outside area | No. |  | 8 |  | 8
x | outer side soling | sqm |  | 140 | 80 | 220
11 | RWTP
a | Footing excavation | no | 10 | 10 | 0 | 10
b | PCC in footings | no | 10 | 10 | 0 | 10 | 0
c | RCC footings | no | 10 | 10 | 0 | 10 | 0
d | Columns pesestal | no | 10 | 10 | 0 | 10 | 0
e | Slab of DC | no | 2 | 2 |  | 2
f | Column above Slab of DC | no | 4 | 4 |  | 4
| column above lintel in Panel Room | no | 6 | 6 |  | 6
g | Tank Excavation | no | 4 | 4 | 0 | 4 | 0
h | Tank PCC | no | 4 | 4 | 0 | 4 | 0
i | Tank raft | no | 4 | 4 | 0 | 4 | 0
j | Tank wall/pedestal | no | 4 | 4 | 0 | 4
k | Clarified water tank/ raft | no | 1 | 1 |  | 1
l | Clarified water tank/wall 1st lift | Cum. | 8.5 | 8.44 |  | 8.44
m | Clarified water tank/wall 2nd lift | Cum. | 8.5 | 8.5 |  | 8.5
| Clarified Water Tank Slab | Cum | 11.5 | 11.35 |  | 11.35
n | Pump Foundation P.C.C. | no |  | 2 |  | 2
o | Pump Foundation R.C.C. | no |  | 2 |  | 2
p | Column in panel room | no | 6 | 6 |  | 6
q | Soling under floor | cum |  | 15 |  | 15
r | PCC for floor | cum |  | 28.25 |  | 28.25
s | Grade Slab RCC | cum |  | 45.5 |  | 45.5
t | Dyke Wall | Rmt. |  | 46 |  | 46
u | Tank bitumastic | sqm | 16.6 | 16.6 |  | 16.6 |  | Completed on 24.03.2018
v | Foundation | no |  | 11 |  | 11
x | effluent pit PCC | cum |  | 5.95 |  | 5.95
y | effluent pit Raft | cum |  | 22.97 |  | 22.97
| Effluent pit wall | Cum | 20.5 | 20.5 |  | 20.5
z | Staircase | Cum |  | 16.2 |  | 16.2
A1 | Brick Work | Cum |  | 6 |  | 6
B1 | Plaster | sqm |  | 106.4 |  | 106.4
C1 | Plinth Protection | Cum |  | 7 |  | 7
12 | TG Building
a | Excavation | cum | 1000 | 1000 | 0 | 1000 | 0
b | Pile cap p.c.c. | no. | 26 | 26 |  | 26
c | Pile Cap R.C.C. | no. | 26 | 26 |  | 26
d | Column 1st Lift | No. | 36 | 36 |  | 36
e | Column 2nd Lift | No | 36 | 5 |  | 5
f | Column 3rd Lift | No. |  | 1 |  | 1
g | Column Final Lift | No. |  | 1 |  | 1
h | Plinth beam | RMT |  | 212.5 |  | 212.5
i | Beam at 2.9 mtr | Cum. |  | 5.5 |  | 5.5
j | Transformer P.C.C. | Cum. |  | 1 |  | 1
k | D.G. Foundation | Cum. |  |  | 25.2 | 25.2
13 | Boiler House
a | Pile cap excavation | no | 11 | 11 | 0 | 11
b | Pile cap PCC | no | 11 | 11 | 0 | 11 | 0
c | Pile cap | no | 11 | 11 | 0 | 11
d | Plinth beam P.C.C. | no | 4 | 4 | 0 | 4
e | Plinth Beam R.C.C. | no | 4 | 4 | 0 | 4
f | Pedestal 1st lift | no | 13 | 13 | 0 | 13
g | Pedestal 2nd lift | no | 13 | 13 | 0 | 13
h | Pedestal 3rd lift | no | 3 | 3 | 0 | 3
i | Slab at +2.85 m lvl | Cum |  | 26.75 | 0 | 26.75
j | Column Above Slab 1st lift | no | 10 | 10 | 0 | 10
k | Column Above Slab 2nd lift | no | 10 | 10 | 0 | 10
L | Slab at +5.45 m lvl | Cum | 71 | 71 |  | 71
m | Column Above Slab +5.45 m | no |  | 4 |  | 4
n | Dyke Wall P.C.C. | Rmt |  | 60 |  | 60
0 | Dyke Wall R.C.C. raft | Rmt |  | 60 |  | 60
p | Dyke Wall | Rmt |  | 60 |  | 60
q | Grade Slab P.C.C. | Cum |  | 10.1 |  | 10.1
r | Grade Slab R.C.C.(M-20) | Cum |  | 29 | 15.5 | 44.5
14 | Caustic & Sulphuric
a | Excavation of tank | no | 2 | 2 | 0 | 2
b | P.c.c. of tank | no | 2 | 2 | 0 | 2
c | Raft of tank | no | 2 | 2 | 0 | 2
d | Wall of tank 1st lift | no | 2 | 2 |  | 2
e | Wall of tank 2st lift | no | 2 | 2 |  | 2
f | Dyke Wall P.C.C. | Rmt |  | 45 |  | 45
g | Dyke Wall R.C.C. raft | Rmt |  | 45 |  | 45
h | Dyke Wall 1st Lift | Rmt |  | 45 |  | 45
i | Dyke Wall 2nd Lift | Rmt |  | 45 |  | 45
j | Sand Filling in Tank | No | 2 | 2 |  | 2
k | Grade Slab in Tank | No | 2 | 2 |  | 2
l | Footing P.C.C. | No |  | 3 |  | 3
m | Footing R.C.C. | No |  | 3 |  | 3
n | Pedestal | No |  | 3 |  | 3
o | Floor P.C.C. | Cum |  | 10.2 |  | 10.2
p | Grade Slab | Cum |  | 17 |  | 17
p | Bitumastic pad | No | 2 | 2 |  | 2 |  | Completed on 04.05.2018
q | foundation | No |  | 2 |  | 2
r | Drain | Rmt |  | 8 |  | 8
s | Staircase | Cum |  | 1.7 |  | 1.7
15 | Ammonia Compressor
a | Foundation P.c.c. | no | 12 | 12 |  | 12
b | Foundation R.c.c. | no | 12 | 12 |  | 12
c | Column with bolt | no | 12 | 12 |  | 12
d | Compressor foundation PCC | no | 4 | 4 |  | 4
e | Compressor found. RCC 1st lift | no | 4 | 4 |  | 4
f | Compressor found. RCC 2nd lift | no | 4 | 4 |  | 4
g | Compressor found. RCC Final lift | no | 4 | 4 |  | 4
h | Dyke Wall P.C.C. | Rmt | 42 | 42 |  | 42
i | Dyke Wall Raft | Rmt | 42 | 38 |  | 38
j | Dyke Wall | Rmt | 42 | 38 |  | 38
k | Pump Foundation | No |  | 2 |  | 2
16 | Ammonia Tanker Loading Bay
a | Excavation for Footing | no | 15 | 15 |  | 15
b | Footing PCC | no | 15 | 15 |  | 15
c | RCC footings | no | 15 | 15 |  | 15
d | Pedestal 1st lift | no | 15 | 15 |  | 15
17 | WNA,SNA,CAN Loading Bay
a | Excavation for Footing | no | 15 | 15 |  | 15
b | Footing P.C.C. | no | 15 | 15 |  | 15
c | Footing R.C.C. | no | 15 | 15 |  | 15
d | Pedestal | no | 15 | 15 |  | 15
18 | Ammonia Scrubber
a | Excavation for Footing | no | 6 | 6 |  | 6
b | P.C.C. for Footing | no | 6 | 6 |  | 6
c | R.C.C. for Footing | no | 6 | 4 | 2 | 6
d | Pedestal | no | 6 | 2 | 2 | 4

## machinery
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE:19.06.2018
Machinery Deployment
Sr.No. | CATEGORY | UNIT | QTY. DEPLOYED
1 | JCB | no | 2
2 | Tractor | no | 3
3 | TM | no | 2
4 | Batching plant | no | 1
5 | Concrete pump | no | 1

## material report
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE: 18.06.2018
MATERIAL REPORT
Sr.No. | ITEM | UNIT | QTY. RECEIVED
|  |  | PREVIOUS RECEIVED | TODAY RECEIVED | CUMMULATIVE RECEIVED
1 | TMT BAR
| 8mm | Mt. | 100.964 |  | 100.964
| 10mm | Mt. | 94.37 |  | 94.37
| 12mm | Mt. | 113.1 |  | 113.1
| 16mm | Mt. | 160.74 |  | 160.74
| 20mm | Mt. | 167.48 |  | 167.48
| 25 mm | Mt. | 185.9 |  | 185.9
| 32 mm | Mt. | 26.29 |  | 26.29

## Qty .plan
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE: 19.06.2018
PROGRESS18.06.2018
S.No | Item Description | Unit | Total scope as per BOQ | Additional scope expected in BOQ | Released till date | Cumulative Achieved till last month | This month progress - June 2018 |  |  |  | Cumulative achieved since inception.
[7 empty] | Planned for this month | Till date achieved in this month | Achieved today | Cumulative Achieved till date in this month |  | 2018-07-01
|  | 1 | 2 |  |  | 3 | 4 | 5 | 6 | 7 = 5+6 | 3 + 7
AS PER BOQ
1 | Concrete
a | Concrete -M30 | CUM | 5396 | 2334.5 | 7730.5 | 5799.7 | 450 | 248.5 | 11 | 259.5 | 6059.2 | 400
b | M20 | CUM | 60 | 1744 | 1804 | 296.5 | 20 | 92 |  | 92 | 388.5
c | M10 | CUM | 1597 | 321.6 | 1275.4 | 918.9 | 200 | 125 | 3 | 128 | 1046.9 | 100

## Fabrication Report
PROJECT : CIVIL AND STRUCTURAL WORK FOR NITRIC ACID PLANT PH-2 FOR DAHEJ
AGENCY : KHURANA CONSTRUCTIONS VADODARA
DATE: 19.06.2018
PROGRESS : 018.06.2018
STRUCTURAL STEEL FABRICATION REPORT
PROJECT :- DFPCL |  |  |  | LOCATION :- DAHEJ | [8 empty] | DATE:- | 09.06.2018
BUILDING | SCOPE | UNIT | MATERIAL RECEIVED | FABRICATION |  |  | ERECTION |  |  | ALIGNMENT |  |  | BLASTING | PAINTING
|  |  |  | PREV. | TODAY | CUMM. | PREV. | TODAY | CUMM. | PREV. | TODAY | CUMM. |  | PRIMER | MIO | FINAL COAT
103A - WNA Storage Tank | 5.7 | MT |  | 5.7 |  | 5.7 | 3 |  | 3 | 3 |  | 3 | 5.7 | 5.7 | 5.7 | 5.7
103E - WNA / CNA/SNA Tanker Loading Bay | 13.5 | MT |  | 13.5 |  | 13.5 | 13.5 |  | 13.5 | 13.5 |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
104A -Caustic, Sulphuric Storage | 3 | MT |  | 3 |  | 3 |  | 2 | 2 |  |  | 0 | 3 | 3 | 3 | 3
123-Ammonia Scrubber | 28 | MT |  | 16.5 | 3 | 19.5 |  |  | 0 |  |  | 0 | 11.5 | 11.5 | 11.5 | 11.5
104C -Ammonia Storage | 25 | MT |  | 6 | 1 | 7 |  |  | 0 |  |  | 0 | 3.5 | 3.5 | 3.5 | 3.5
104C -Ammonia Compressor | 11 | MT |  | 10.8 |  | 10.8 | 9 |  | 9 |  |  | 0 | 10.8 | 10.8 | 10.8 | 10.8
104E -SNA Storage | 3.5 | MT |  | 3.3 |  | 3.3 |  |  | 0 |  | 1 | 1 | 3.3 | 3.3 | 3.3 | 3.3
105A/C - Air Compressor, Air Dryer | 13 | MT |  | 12.9 |  | 12.9 | 12.9 |  | 12.9 | 12.9 |  | 12.9 | 12.9 | 12.9 | 12.9 | 12.9
105B - VAM Unit | 15 | MT |  | 15 |  | 15 | 15 |  | 15 | 15 |  | 15 | 15 | 15 | 15 | 15
106C - TG Building | 75 | MT |  | 57.8 | 2 | 59.8 | 29.5 |  | 29.5 | 27 |  | 27 | 57.9 | 55.8 | 55.8 | 55.8
107B - Raw Water Treatment Plant |  | MT |  |  |  | 0 |  |  | 0 |  |  | 0
108C - DM Plant | 2.5 | MT |  | 2.5 |  | 2.5 | 2.5 |  | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
108D - DM STORAGE |  | MT |  |  |  | 0 |  |  | 0 |  |  | 0
109 - Cooling Tower with Pumps |  | MT |  |  |  | 0 |  |  | 0 |  |  | 0
110 - Process Substation/DG ROOM | 2 | MT |  | 0.6 |  | 0.6 | 0.6 |  | 0.6 |  |  | 0 | 0.6 | 0.6 | 0.6 | 0.6
TOTAL | 197.2 |  |  | 147.6 | 6 | 153.6 | 86 | 2 | 88 | 73.9 | 1 | 74.9 | 140.2 | 138.1 | 138.1 | 138.1
Description | FABRICATION Current Manpower | ERECTION Current Manpower |  | Remarks :
Fitter | 3 | 2
Welder | 3 | 1
Gas Cutter | 2
Grinder | 2
Driller | 2
Helper | 2
Rigger | 6 | 8
Tack welder | 1
Sandblasting | 1
Painting | 2
Foremen | 1
Total | 25 | 11